## Scheduling
Iteration No | Task No | Description | Planned Start Date / Time | Planned End Date / Time | Hours Planned | Actual Start Date / Time | Actual End Date / Time | Actual Hours Spent | Location | Status | Done By (Use Initials. Leader in bold)
1 | 1 | Read Project Wiki Individually | 2019-09-04/ 19:45 | 2019-09-08/ 23:59 | 2 | 2019-09-07 | 2019-09-08 | 1.5 | Home OTOT | Completed | JX,AW,TB,JH,ZH
1 | 2 | Clarify doubts on the requirements Allocate tasks | 2019-09-09/ 15:00 | 2019-09-09/ 17:00 | 2 | 2019-09-09/ 15:00 | 2019-09-09/ 17:00 | 1.5 | SOE/SOSS GSR 2- 14 | Completed | JX,AW,TB,JH,ZH
1 | 3 | Attempt to start coding (login) | 2019-09-16/ 1530 | 2019-09-16/ 17:00 | 2
1 | 4 | Actual Scheduling | 2019-09-23/ 15:30 | 2019-09-23/ 17:00 | 2
1 | 5

## Role Allocation
Iterations | Project Manager | Programmer | Programmer | Login
1 | Andrew | Zhenhui, Jiaxin | Thao, Jia Hui | week 4- 6
2 | Thao | Zhenhui, Andrew | Jiaxin, Jia Hui | week 6 - 8 | week 7 - Interim
3 | Jia Xin | Thao, zhen hui | Andrew, Jia Hui | week 8- 10 | week 9 - demo
4 | Jia Hui | Andrew, Thao | Jiaxin, Zhenhui | week 10-12 | week 12 - UAT
5 | Zhen Hui |  |  | Week 12-14 | week 14 - Presentation

## Team Schedule
| Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
8.15am - 11.30am |  | (Jia Xin) COR1305 | (Andrew) COR1305 (Jiahui) STAT1202 | (Andrew) IS211 (Zhen Hui) IS210 (Jia Hui) IS211 (Jia Xuan) COR-IS1702
12.00pm - 3.15pm. | (Zhen Hui) STAT 1202 | (Andrew) FTW200 *first 5 weeks | (Thao) IS211 | (Jia Hui) FTW *first 5 weeks | (Thao) MC (Jia Hui) CT
3.30pm-6.45pm |  | (Thao) FTW200 *first five weeks | (All) IS212 | (Thao) STATS (Zhen Hui) IS211 (Jia Xin) IS210 | (Jia Xin) OCSP
7.00pm-10.15pm |  |  |  |  | (Zhen Hui) CSP (7-9PM)