## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | Login (User & Admin) | Undefined variable. Cannot fetch the username data from the studentDAO | High | 5 | 51 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
2 | 1 | Login (User) | Failed opening required autoload.php breakdown for login page | Critical | 10
3 | 1 | Login (User & Admin) | username left blank but password is written inputed Fatal error: Call to a member function getUserID() on null | High | 5 |  | Use the planned debugging time in the iteration.
4 | 1 | Login (User & Admin) | Clicked on submit button without entering values into the fields Fatal error: Call to a member function getUserID() on null | High | 5
5 | 1 | Login (User & Admin) | Failed to retrieve data because the whole database data could not be inserted (bootstrap) | High | 5
6 | 1 | studentpage.php (after login) | Unable to fetch the data of the remaining bids because bid functions are incomplete | Low | 1
7 | 1 | Login (User & Admin) | Fatal error: Call to a member function authenticate on null () - password_verify() cannot be used on non-hashed password | High | 5
8 | 1 | Bootstrap | When importing Sample Data.Zip, unexpected '-> Parse Error for one member laptop | Critical | 10 |  | Use the planned debugging time in the iteration.
9 | 1 | Bootstrap | The result message is not the same as the one in the requirements document | Low | 1
10 | 1 | Login (User) | Database mismatch between bootstrap and login | Low | 1 |  | Change the database name in bootstrap from sampledata to spm_database
11 | 1 | Bootstrap | When trying to bootstrap file with section code exceeds 3 characters => error => SQL script for table section has error | Low | 1
12 | 1 | Bootstrap | Undefined variable student_school. Cannot access property edollar of a non-object | Low | 1
13 | 1 | Bootstrap | Trying to get property 'day' of non-object | Low | 1
1 | 3 | Bid for section(round 1) | Require_once(Bid.php) is not existing in the project\app\login page\model\common.php | Critical | 10 | 37
2 | 3 | Bid for section(round 2) | Able to bid for courses lower than minimum bid | High | 5
3 | 3 | Bootstrap | missing order of the error | Low | 1 |  | Include sort in bootstrap file
4 | 3 | JSON Web Service | missing field validation | High | 5 |  | Include field validation
5 | 3 | JSON Web Service | missing token validation | High | 5 |  | Include token validation
6 | 3 | JSON Web Service (Update-bid) | missing logic validation in update-bid (no vacancy, course enrolled) | Low | 1 |  | Include login validation
7 | 3 | JSON Web Service (Update-bid) | Syntax error | Low | 1 |  | Missing semicolon -> add semi colon
8 | 3 | JSON Web Service (User-dump) | Undefined function verify_token | Low | 1 |  | Include token.php
9 | 3 | JSON Web Service (User-dump) | Undefined variable result | Low | 1 |  | Change result to message
10 | 3 | JSON Web Service (User-dump) | Result for student's edollar didn't show as requested | Low | 1 |  | Change the type of student's edollar to float
11 | 3 | Bootstrap | The student's edollar is not deducted after successfully bidded a section | Low | 1 |  | Deduct student's edollar in bootstrap file
12 | 3 | JSON Web Service (update-bid) | Undefined offset on round_2.php | High | 5
1 | 4 | JSON Web Serivce (Bid-Status) | Syntax error for output (e.g. output of balance not suppose to have "10.00 " instead, 10.0 | High | 5 | 58 | Added float() and int() in bid-status.php
2 | 4 | Round 1 Clearing Logic | The number of students bid at clearing price is 1 but he is not successful | High | 5 |  | Change the logic in bootstrap.php
3 | 4 | JSON Web Service (stop) | Trying to get property of non-object | High | 5 |  | Change the calling function from calling the nested array instead of the whole array of object
4 | 4 | JSON Web Service (section-dump) | Undefined variable 'result' | High | 5 |  | Add variable 'result' and changed the output result of the round 1
5 | 4 | JSON Web Service (update-bid) | Wrong sequence of output | Low | 1 |  | Change the order of the error message
6 | 4 | JSON Web Service (update-bid) | Additional error message | Low | 1 |  | Change the logic of processing errors
7 | 4 | Bootstrap | Allow 'S01' to pass | High | 5 |  | Change the processing logic in bootstrap
8 | 4 | JSON Web Service (Update-bid) | Problem with cheking exam timetable clash | High | 5 |  | Change the checking logic for exam timetable
9 | 4 | Bootstrap | Allow 'S 9 8' to pass | High | 5 |  | Change the processing logic in bootstrap
10 | 4 | Bootstrap | Wrong sequence of output | Low | 1 |  | Change the sequence of logic and common validation
11 | 4 | Bootstrap | When there is blank field, only output 'blank field', not output the name of the field | High | 5 |  | Change the sequence of logic and common validation
12 | 4 | Bootstrap | When the student wants to update his bid -> the system doesn’t drop the previous bid when all the validations are correct | High | 5 |  | Change the function "DropSpecficBid"
13 | 4 | Place Bid | If the input is lowercase, the bid will not pass due to invalid section/course (case-sensitivity issue) | High | 5 |  | Add strtoupper
14 | 4 | Bootstrap | Wrong error message for incomplete prerequisite | High | 5 |  | Change the order of course completed validation and incomplete prerequisite validation

## Bug Log
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team)
1 | 1 | Login (User & Admin) | Undefined variable. Cannot fetch the username data from the studentDAO | Resolved | 2019-09-18 | 2019-09-18 | Jiaxin & Zhen Hui
2 | 1 | Login (User) | Failed opening required autoload.php breakdown for login page | Resolved | 2019-09-23 | 2019-09-23 | Jiaxin & Zhen Hui
3 | 1 | Login (User & Admin) | username left blank but password is written inputed Fatal error: Call to a member function getUserID() on null | Resolved | 2019-09-24 | 2019-09-26 | Jiaxin & Zhen Hui
4 | 1 | Login (User & Admin) | Clicked on submit button without entering values into the fields Fatal error: Call to a member function getUserID() on null | Resolved | 2019-09-24 | 2019-09-26 | Jiaxin & Zhen Hui
5 | 1 | Login (User & Admin) | Failed to retrieve data because the whole database data could not be inserted (bootstrap) | Resolved | 2019-09-26 | 2019-09-26 | Jiaxin & Zhen Hui
6 | 1 | studentpage.php (after login) | Unable to fetch the data of the remaining bids because bid functions are incomplete | Unresolved | 2019-09-26 |  | Jiaxin & Zhen Hui
7 | 1 | Login (User & Admin) | Fatal error: Call to a member function authenticate on null () - password_verify() cannot be used on non-hashed password | Resolved | 2019-09-23 | 2019-09-26 | Jiaxin & Zhen Hui
8 | 1 | Bootstrap | When importing Sample Data.Zip, unexpected '-> Parse Error for one member laptop | Resolved | 2019-09-30 | 2019-09-30 | Zhen Hui
9 | 1 | Bootstrap | The result message is not the same as the one in the requirements document | Resolved | 2019-09-30 | 2019-09-30 | Jia Hui & Thao
10 | 1 | Login (User) | Database mismatch between bootstrap and login | Resolved | 2019-09-30 | 2019-09-30 | Jia Hui & Thao
11 | 1 | Bootstrap | When trying to bootstrap file with section code exceeds 3 characters => error => SQL script for table section has error | Resolved | 2019-09-30 | 2019-09-30 | Jia Hui & Thao
12 | 1 | Bootstrap | Undefined variable student_school. Cannot access property edollar of a non-object | Resolved | 2019-09-30 | 2019-09-30 | Jia Hui & Thao
13 | 1 | Bootstrap | Trying to get property 'day' of non-object | Resolved | 2019-10-01 | 2019-10-01 | Jia Hui & Thao
1 | 3 | Bid for section(round 1) | Require_once(Bid.php) is not existing in the project\app\login page\model\common.php | Resolved | 2019-10-25 | 2019-10-25 | Jiaxin & Andrew
2 | 3 | Bid for section(round 2) | Able to bid for courses lower than minimum bid | Resolved | 2019-10-28 | 2019-10-28 | Jiaxin & Zhen Hui
3 | 3 | Bootstrap | missing order of the error | Resolved | 2019-10-28 | 2019-10-28 | Andrew&Thao
4 | 3 | JSON Web Service | missing field validation | Resolved | 2019-10-28 | 2019-10-28 | Andrew&Thao
5 | 3 | JSON Web Service | missing token validation | Resolved | 2019-10-28 | 2019-10-28 | Andrew&Thao
6 | 3 | JSON Web Service (Update-bid) | missing logic validation in update-bid (no vacancy, course enrolled) | Resolved | 2019-10-28 | 2019-10-28 | Andrew&Thao
7 | 3 | JSON Web Service (Update-bid) | Syntax error | Resolved | 2019-10-28 | 2019-10-28 | Andrew&Thao
8 | 3 | JSON Web Service (User-dump) | Undefined function verify_token | Resolved | 2019-10-29 | 2019-10-29 | Andrew&Thao
9 | 3 | JSON Web Service (User-dump) | Undefined variable result | Resolved | 2019-10-29 | 2019-10-29 | Andrew&Thao
10 | 3 | JSON Web Service (User-dump) | Result for student's edollar didn't show as requested | Resolved | 2019-10-29 | 2019-10-29 | Andrew&Thao
11 | 3 | Bootstrap | The student's edollar is not deducted after successfully bidded a section | Resolved | 2019-10-30 | 2019-10-30 | Jiaxin&Zhenhui
12 | 3 | JSON Web Service (update-bid) | Undefined offset on round_2.php | Resolved | 2019-10-30 | 2019-10-30 | Andrew&Thao
1 | 4 | JSON Web Serivce (Bid-Status) | Syntax error for output (e.g. output of balance not suppose to have "10.00 " instead, 10.0 | Resolved | 2019-11-09 | 2019-11-09 | Zhen Hui & Thao
2 | 4 | Round 1 Clearing Logic | The number of students bid at clearing price is 1 but he is not successful | Resolved | 2019-11-13 | 2019-11-13 | Jiahui&Andrew
3 | 4 | JSON Web Service (stop) | Trying to get property of non-object | Resolved | 2019-11-13 | 2019-11-13 | Zhen Hui & Thao
4 | 4 | JSON Web Service (section-dump) | Undefined variable 'result' | Resolved | 2019-11-13 | 2019-11-13 | Zhen Hui & Thao
5 | 4 | JSON Web Service (update-bid) | Wrong sequence of output | Resolved | 2019-11-13 | 2019-11-13 | Zhen Hui & Thao
6 | 4 | JSON Web Service (update-bid) | Additional error message | Resolved | 2019-11-13 | 2019-11-13 | Zhen Hui & Thao
7 | 4 | Bootstrap | Allow 'S01' to pass | Resolved | 2019-11-13 | 2019-11-13 | Zhen Hui & Thao
8 | 4 | JSON Web Service (Update-bid) | Problem with cheking exam timetable clash | Resolved | 2019-11-13 | 2019-11-13 | Zhen Hui & Thao
9 | 4 | Bootstrap | Allow 'S 9 8' to pass | Resolved | 2019-11-13 | 2019-11-13 | Zhen Hui & Thao
10 | 4 | Bootstrap | Wrong sequence of output | Resolved | 2019-11-13 | 2019-11-13 | Zhen Hui & Thao
11 | 4 | Bootstrap | When there is blank field, only output 'blank field', not output the name of the field | Resolved | 2019-11-13 | 2019-11-13 | Zhen Hui & Thao
12 | 4 | Bootstrap | When the student wants to update his bid -> the system doesn’t drop the previous bid when all the validations are correct | Resolved | 2019-11-13 | 2019-11-13 | Zhen Hui & Thao
13 | 4 | Place Bid | If the input is lowercase, the bid will not pass due to invalid section/course (case-sensitivity issue) | Resolved | 2019-11-13 | 2019-11-13 | Jiahui&Andrew
14 | 4 | Bootstrap | Wrong error message for incomplete prerequisite | Resolved | 2019-11-13 | 2019-11-13 | Zhen Hui & Thao