## Week 5
Person | Question | Week: <16/9/2019> to <22/9/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Andrew Woon (AW) | What did you do yesterday? |  |  |  | Finished Scheduling up to Iteration 2 scheduling | Update schedule, updated DU. | Update schedule, updated DU. | Not a working day
| What will you do today? |  |  |  | Complete scheduling | Port over data to new schedule required as of 19/9 | Not a working day | Not a working day
| Do you have any obstacles? |  |  |  | Need to clarify if PM daily updates have to be included | No issues | No issues | Not a working day
Thao (TH) | What did you do yesterday? |  |  |  | Not a working day | Not a working day | Finish bootstrap validation for course.csv and section.csv with Jiahui | Not a working day
| What will you work on today? |  |  |  | Not a working day | Finish bootstrap validation for course.csv and section.csv with Jiahui | Not a working day | Finish bootstrap validation for prerequisite.csv and course_completed.csv with Jiahui
| Do you have any obstacles? |  |  |  | No Issues | No issues | I had something last minute so the pp session started later, at 6 | Nope
Jia Xin (JX) | What did you do yesterday? |  |  |  | Login Page | Not a working day | Not a working day | Not a working day
| What will you work on today? |  |  |  | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? |  |  |  | No issues | No issues | Nope | Not a working day
Jia Hui (JH) | What did you do yesterday? |  |  |  | Not a working day | Not a working day | Finish bootstrap validation for course.csv and section.csv with Thao | Not a working day
| What will you work on today? |  |  |  | Not a working day | Finish bootstrap validation for course.csv and section.csv with Thao | Not a working day | Finish bootstrap validation for prerequisite.csv and course_completed.csv with Thao
| Do you have any obstacles? |  |  |  | No issues | No issues | Nope | Nope
Zhen Hui (ZH) | What did you do yesterday? |  |  |  | Login Page | Not a working day | Not a working day | Not a working day
| What will you work on today? |  |  |  | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? |  |  |  | No issues | No issues | No issues | No issues

## Week 6
Person | Question | Week: <23/9/2019> to <29/9/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Andrew Woon (AW) | What did you do yesterday? | Not a working day. | Discuss/edit schedule | Update schedule/attempt to calculate critical path | Brief team on Bug Matrix Clarify DU timings/crit path with prof | Not a working day | Update schedule | Not a working day
| What will you do today? | Discuss and edit schedule | Update schedule | Brief team on Bug Matrix Clarify DU timings/crit path with prof | Not a working day | Update Schedule | Not a working day | Not a working day
| Do you have any obstacles? | none | None | None | None | None | None | None
Thao (TH) | What did you do yesterday? | Finish bootstrap validation for prerequisite .csv and course_completed.csv with Jiahui | Finish bootstrap validation for student .csv and half of the validation for bid.csv with Jiahui | Finish boostrap validation for bid.csv with Jiahui | Not a working day | Not a working day | Update schedule | Not a working day
| What will you work on today? | Finish bootstrap validation for student .csv and bid.csv with Jiahui | Finish the other half of bootstrap validation for bid.csv with Jiahui | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | Nope | Nope | None | no | None | Nope | None
Jia Xin (JX) | What did you do yesterday? | Not a working day. | Debug login function | Meet with Zhen Hui to debug | Validation of login page, retrieve student info to after login with zhenhui | Validation of login page, retrieve student info after login with zhenhui | although Not a working day , However, decided to enhance login function by hashing pw, add authenticate functions with zhenhui - testing -styling of html | Not a working day
| What will you work on today? | Finish up the login function and debug if possible with zhenhui | Pair programming with Zhenhui | Do authenticate page | continue with what is left from ytd with zhenhui | Testing for login | Not a working day | Not a working day
| Do you have any obstacles? | Not a working day | Some problems with auto loading | None | figuring out the logic for all possible validation was time consuming and took up most of the time -lack of time to do due to other midterms and commitment (hence delay) | - | - | None
Jia Hui (JH) | What did you do yesterday? | Finish bootstrap validation for prerequisite .csv and course_completed.csv with Thao | Finish bootstrap validation for student .csv and half of the validation for bid.csv with Thao | Finish boostrap validation for bid.csv with Thao | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Finish bootstrap validation for student .csv and bid.csv with Thao | Finish the other half of bootstrap validation for bid.csv with Thao | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | Nope | Nope | None | No | None | None | None
Zhen Hui (ZH) | What did you do yesterday? | Not a working day. | Debug login function | Discuss validation logic and starting to do retrieving of edollar aft login with jiaxin | Validation of login page, retrieve student info to after login with jiaxin | Validation of login page, retrieve student info after login with jiaxin | although Not a working day , However, decided to enhance login function by hashing pw, add authenticate functions with zhenhui - testing -styling of html | Not a working day
| What will you work on today? | Finish up the login function and debug if possible with jiaxin | - add welcome msg, retrieve edollar, add logout button for after login page at studentpage.php - proceed to validation at login.php - logout page at admin - fixed bugs for validation | Continue to do the tasks that are yet to finish from ytd | continue with what is left from ytd with jiaxin | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | No issues | Difficult to debug the login function because of minor typos and wrong use of function | None | '-figuring out the logic for all possible validation was time consuming and took up most of the time -lack of time to do due to other midterms and commitment (hence delay) | - | - | None

## Week 7
Person | Question | Week: <30/9/2019> to <6/10/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Andrew Woon (AW) | What did you do yesterday? | Not a Working Day | Did slides with group Calculate critical path | PM review slides (Schedule) | PM Review PM Review debrief | Not a working day | Not a working day | Not a working day
| What will you do today? | PM review slides Test functions | PM review slides (Schedule) | PM Review | Not a Working Day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | None | None | None | None | Nope | None
Thao (TH) | What did you do yesterday? | Not a working day | Pm review slides tgt with grp Create testcases with Jiahui | Debug and rerun testcases with Jiahui | Ask Prof about the utf8mb4 characters set in MySQL PM Review | Not a working day | Not a working day | Not a working day
| What will you work on today? | Pm review slides tgt with grp Create testcases with Jiahui | Debug and rerun testcases with Jiahui | Ask Prof about the utf8mb4 characters set in MySQL PM Review | Not a working day | Not a working day | Not a working day | Re-calculate critical path
| Do you have any obstacles? | None | None | None | None | Nope | Nope | None
Jia Xin (JX) | What did you do yesterday? | Not a working day | Pm review slides tgt with grp | Updated testcases AWS integration | PM Review | Not a working day | Not a working day | Not a working day
| What will you work on today? | Pm review slides tgt with grp | Not a working day | PM Review | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | None | None | None | No | No | None
Jia Hui (JH) | What did you do yesterday? | Not a working day | Pm review slides tgt with grp Create testcases with Thao | Debug and rerun testcases with Thao | PM Review | Not a working day | Not a working day | Not a working day
| What will you work on today? | Pm review slides tgt with grp Create testcases with Thao | Debug and rerun testcases with Thao | Pm Review | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | None | Nope | None | Nope | Nope | None
Zhen Hui (ZH) | What did you do yesterday? | Not a working day | Pm review slides tgt with grp | Update testcases | PM Review | Not a working day | Not a working day | Not a working day
| What will you work on today? | Pm review slides tgt with grp | Not a working day | PM Review | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | None | Nope | None | No | No | No

## Week 8
Person | Question | Week: <7/10/2019> to <13/10/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Andrew Woon (AW) | What did you do yesterday? | Not a working day | Plan for iter 2 with team Start closing/clearing round 1 with Thao | Continue closing rounds with JiaXin | Continue closing rounds | Finish round 1 clearing logic with JiaXin | Round 2 clearing logic with JiaXin | Not a working day
| What will you do today? | Plan for iter 2 with team | Continue closing/clearing rounds with jia xin | Continue closing rounds with JiaXin | Complete closing rounds | Start round 2 | Not a working day | Not a working day
| Do you have any obstacles? | None | None | Unable to complete closing rounds, will continue today | None | No | No | No
Thao (TH) | What did you do yesterday? | Not a working day | Plan for iter 2 with team Start round 1 with Andrew | Not a working day | Not a working day | Update schedule | Not a working day | Not a working day
| What will you work on today? | Plan for iter 2 with team | Not a working day | Not a working day | Update schedule | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | None | None | No | No | No | No
Jia Xin (JX) | What did you do yesterday? | Not a working day | Plan for iter 2 with team | Continue closing rounds with Andrew | Continue closing rounds | Finish round 1 clearing logics with Andrew | Round 2 clearing logic with Andrew | Not a working day
| What will you work on today? | Plan for iter 2 with team | Continue closing/clearing rounds with Andrew | Continue closing rounds with Andrew | Complete closing rounds | Insert sql table and integrate Start round 2 | Not a working day | Not a working day
| Do you have any obstacles? | None | None | Unable to complete closing rounds, will continue today | None | No | No | No
Jia Hui (JH) | What did you do yesterday? | Not a working day | Plan for iter 2 with team Start bid for a section with zh | Continue bid for a section with ZhenHui | Not a working day | Continue bid for a section with Zhenhui | continue validation for bidding a section with Zhenhui integration of admin's clearing logic and student's bidding for a section with the team | Not a working day
| What will you work on today? | Plan for iter 2 with team | Continue doing bid for a section with zh | Not a working day | Continue bid for a section with zhenhui | continue validation for bidding a section with Zhenhui integration of admin's clearing logic and student's bidding for a section with the team | Not a working day | Complete 2 more validations for bid for a section and finish drop bid function with zhenhui
| Do you have any obstacles? | None | None | Unable to complete bid for a section | No | difficult to visualize the validation logic | No | No
Zhen Hui (ZH) | What did you do yesterday? | Not a working day | Plan for iter 2 with team Start bid for a section with jiahui | Continue bid for a section with jiahui | Not a working day | Continue bid for a section with Jiahui | continue validation for bidding a section with jiahui integration of admin's clearing logic and student's bidding for a section with the team | Not a working day
| What will you work on today? | Plan for iter 2 with team | Continue doing bid for a section with jiahui | Not a working day | Continue bid for a section with jiahui | continue validation for bidding a section with jiahui integration of admin's clearing logic and student's bidding for a section with the team | Not a working day | Complete 2 more validations for bid for a section and finish drop bid function with jiahui
| Do you have any obstacles? | None | No | Unable to complete bid for a section | No | difficult to visualize the validation logic | No | No

## Week 9
Person | Question | Week: <14/10/2019> to <20/10/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Andrew Woon (AW) | What did you do yesterday? | Not a working day | Round 2 clearing logic Prep for online review | Finished round 2 clearing logic Online review | Online pm review Attempted to integrate | Revised HTML tables | Not a working day | Not a working day
| What will you do today? | Finish round 2 with jia xin Integration and tests Prepare for online review | Finish round 2 clearing logic Meet team to prepare slides | Online review Attempt to integrate | Revise on HTML tables | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | No | Unsure how to integrate round 2 | None | None | None | None | None
Thao (TH) | What did you do yesterday? | Not a working day | Integration and test function with group Prepare for Application Demo and Progress Update | meeting with the team to prepare slides | Online pm review | Not a working day | Not a working day | Not a working day
| What will you work on today? | Integration and test function with group Prepare for Application Demo and Progress Update | meeting with the team to prepare slides | Online review Debrief | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | Not a working day | None | None | None | None | None | None
Jia Xin (JX) | What did you do yesterday? | Not a working day | Integration and test function with group round 2 clearing logic | Finished round 2 clearing logic Online review | Online pm review Attempted to integrate | Not a working day | Not a working day | Not a working day
| What will you work on today? | Finish round 2 with andrew Integration and tests Prepare for online review | meeting with the team to prepare slides Finish round 2 clearing logic | Online review Attempt to integrate | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | No | None | None | None | None | None | None
Jia Hui (JH) | What did you do yesterday? | Finish up validations for bid for a section and do drop bid function | Integration and test function with group Prepare for Application Demo and Progress Update | not a working day | Online pm review | Not a working day | Not a working day | Not a working day
| What will you work on today? | Integration and test function with group Prepare for Application Demo and Progress Update | meeting with the team to prepare slides | Online review | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | No | None | None | None | None | None | None
Zhen Hui (ZH) | What did you do yesterday? | Finish up validations for bid for a section and do drop bid function | Integration and test function with group Prepare for Application Demo and Progress Update | meeting with the team to prepare slides | Online pm review | Not a working day | Not a working day | Not a working day
| What will you work on today? | Integration and test function with group Prepare for Application Demo and Progress Update | meeting with the team to prepare slides | Online review | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | No | None | None | None | None | None | None

## Week 10
Person | Question | Week: <21/10/2019> to <27/10/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Andrew Woon (AW) | What did you do yesterday? | Not a working day | Json for Authenticate Started View-bids with Thao | Not a working day | View bids, json web service with Thao | Complete view bids result with Andrew | Debugging session with JiaXin | Not a working day
| What will you do today? | View-bids with Thao | Not a working day | View bids, json web service with Thao | Complete view bids result | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | No | Having error for view-bid due to 2 common php | No | No | No | No | No
Thao (TH) | What did you do yesterday? | Not a working day | Json for Authenticate Started View-bids with Andrew | Not a working day | View bids, json web service with Andrew | Complete view bids result with Andrew | Not a working day | Not a working day
| What will you work on today? | View-bids with Andrew | Not a working day | View bids, json web service with Andrew | Complete view bids result | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | No | Having error for view-bid due to 2 common php | No | No | No | No | No
Jia Xin (JX) | What did you do yesterday? | Not a working day | Login token with zhenhui Json checker for authenticate | Not a working day | Drop section with Zhenhui | Not a working day | Added in test cases for bid a section Debugging session with Andrew | Enhance UI
| What will you work on today? | Login token with zhenhui | Not a working day | Drop section with ZhenHui | Not a working day | Test cases for drop a section and bid a section | Enhance UI | Manual testing for bid and drop section
| Do you have any obstacles? | No | No | No | No | No | No | No
Jia Hui (JH) | What did you do yesterday? | Not a working day | Discuss and edit schedule | Not a working day | Update schedule | Not a working day | Not a working day | Update schedule
| What will you work on today? | Discuss and edit schedule | Not a working day | Update schedule | Not a working day | Not a working day | Update schedule | Not a working day
| Do you have any obstacles? | No | No | No | No | No | No | No
Zhen Hui (ZH) | What did you do yesterday? | Not a working day | Login token with jiaxin Json checker for authenticate | Not a working day | Drop section with JiaXin | Not a working day | Not a working day | Do auto testing
| What will you work on today? | Login token with jiaxin | Not a working day | Drop section with JiaXin | Not a working day | Not a working day | Enhance UI, do auto testing | Enhance UI
| Do you have any obstacles? | No | No | No | No | No | No | No

## Week 11
Person | Question | Week: <28/10/2019> to <3/11/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Andrew Woon (AW) | What did you do yesterday? | Not a working day | Prepare for UAT Debug view bid/round codes with Thao | Testing/debug | Debug AWS deployment UAT Presentation | Not a working day | Not a working day | Not a working day
| What will you do today? | Testing/Debug with Thao Prepare for UAT | Test round codes | Debug AWS deployment UAT Presentation | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | No | No | No | No | No | No | No
Thao (TH) | What did you do yesterday? | Not a working day | Prepare for UAT Testing/Debugging with Andrew | Testing/debug | Debug AWS deployment UAT Presentation | Not a working day | Not a working day | Not a working day
| What will you work on today? | Testing/Debug with Andrew Prepare for UAT | Testing | Debug AWS deployment UAT Presentation | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | No | No | No | No | No | No | No
Jia Xin (JX) | What did you do yesterday? | Enhance UI Added in test cases for bid and drop section | Prepare for UAT Debugging for bid for a section errors | Debug | Aws deployment UAT presentation | Not a working day | Not a working day | Not a working day
| What will you work on today? | Fix errors from bid and drop sections with ZhenHui Finish test cases for drop and bid sections Prepare for UAT | AWS Deployment | Aws deployment UAT presentation | Not a working day | Not a working day | Not a working day | scheduling
| Do you have any obstacles? | No | No | No | No | No | No | No
Jia Hui (JH) | What did you do yesterday? | Not a working day | Prepare for UAT | Update schedule | Aws deployment UAT presentation | Not a working day | Not a working day | Not a working day
| What will you work on today? | Prepare for UAT | Update schedule | Aws deployment UAT presentation | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | No | No | No | No | No | No | No
Zhen Hui (ZH) | What did you do yesterday? | Enhance UI | Prepare for UAT Debugging for bid for a section errors | Debug | Aws deployment UAT presentation | Not a working day | Not a working day | Not a working day
| What will you work on today? | Fix errors from bid and drop sections with JiaXin Prepare for UAT | AWS Deployment | Aws deployment UAT presentation | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | No | No | No | No | No | No | No

## Week 12
Person | Question | Week: <4/11/2019> to <10/11/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Andrew Woon (AW) | What did you do yesterday? | Not a working day | Debugging session | Not a working day | Debug of round clearing logic with jia hui | Debugging session | Not a working day | Not a working day
| What will you do today? | Debugging session | Not a working day | Debugging session | Debugging session | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | No | No | No | No | No | No | No
Thao (TH) | What did you do yesterday? | Not a working day | Debugging session | Not a working day | Bid status and debugging of json with zhenhui | Not a working day | Not a working day | Not a working day
| What will you work on today? | Debugging session | Not a working day | Bid status function | Not a working day | Not a working day | Not a working day | Testing for bid status
| Do you have any obstacles? | No | No | No | No | No | No | No
Jia Xin (JX) | What did you do yesterday? | scheduling | Discuss and edit schedule | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Discuss and edit schedule | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | No | No | No | No | No | No | No
Jia Hui (JH) | What did you do yesterday? | Not a working day | Debugging session | Not a working day | Debug of round clearing logic with Andrew | Debugging session | Not a working day | Not a working day
| What will you work on today? | Debugging session | Not a working day | Debugging session | Debugging session | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | No | No | No | No | No | No | No
Zhen Hui (ZH) | What did you do yesterday? | Not a working day | Debugging session | Not a working day | Bid status and debugging of json with Thao | Not a working day | Not a working day | Not a working day
| What will you work on today? | Debugging session | Not a working day | Bid status function | Not a working day | Not a working day | Not a working day | Testing for bid status
| Do you have any obstacles? | No | No | No | No | No | No | No

## Week 13
Person | Question | Week: <11/11/2019> to <17/11/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Andrew Woon (AW) | What did you do yesterday? | Not a working day | Debugging and test cases | Not a working day | Regression testing / debugging | Not a working day | Not a working day | Aws deployment, testing
| What will you do today? | Debugging and test cases | Not a working day | Debugging + preparation for slides | Not a working day | Not a working day | Aws deployment & testing | Vetting of final presentation slides
| Do you have any obstacles? | No | No | No | No | No | No | No
Thao (TH) | What did you do yesterday? | Testing for bid status | Debugging | Not a working day | Debugging | Not a working day | Not a working day | Aws deployment, testing
| What will you work on today? | Debugging | Not a working day | Debugging | Not a working day | Not a working day | Aws deployment & testing | Vetting of final presentation slides
| Do you have any obstacles? | No | No | No | No | No | No | No
Jia Xin (JX) | What did you do yesterday? | Not a working day | Final presentation slide | Not a working day | Final presentation slides | Not a working day | Not a working day | Aws deployment, testing
| What will you work on today? | Final presentation slide | Not a working day | Presentation slides | Not a working day | Not a working day | Aws deployment & testing | Vetting of final presentation slides
| Do you have any obstacles? | No | No | No | No | No | No | No
Jia Hui (JH) | What did you do yesterday? | Not a working day | Debugging and test cases | Not a working day | Regression testing / debugging | Not a working day | Not a working day | Aws deployment, testing
| What will you work on today? | Debugging and test cases | Not a working day | Debugging + preparation for slides | Not a working day | Not a working day | Aws deployment & testing | Vetting of final presentation slides
| Do you have any obstacles? | No | No | No | No | No | No | No
Zhen Hui (ZH) | What did you do yesterday? | Testing for bid status | Debugging | Not a working day | Debugging | Not a working day | Not a working day | Aws deployment, testing
| What will you work on today? | Debugging | Not a working day | Debugging | Not a working day | Not a working day | Aws deployment & testing, update schedule | Vetting of final presentation slides
| Do you have any obstacles? | No | No | No | No | No | No | No