## Slide 1: SPM G3T8
Andrew | Thao | Jia Xin | Jia Hui | Zhen Hui

## Slide 2: 1. Functionalities

## Slide 3: 1. Functionalities
Do you plan to drop any functionalities?
Do you plan to add any functionalities?
We are not going to drop any functionalities
Course Search Function
Student Schedule*
Exam Schedule*

## Slide 4
Do you plan to use any PHP frameworks?
No !

## Slide 5: Did you manage to finish login + 1 functionality?
YES !
Notes: Have yet to integration features

## Slide 6: What functionalities have you finished?
Login
Bootstrap

## Slide 7
What is the IP address & admin password for your cloud deployment?
IP: 3.1.101.8
Admin password: Hello123

## Slide 8: 2. Schedule

## Slide 9: Iterations
1
2
3
4
5
18/9 – 2/10
3/10 – 16/10
31/10 – 13/11
14/11 – 20/11
17/10 – 30/10

## Slide 10
Iteration 1 (18/9 – 2/10)
Plan Project (PM + inputs from everyone)
Login Feature (JX – ZH)
Admin Features – bootstrap (TB-JH)
Create Test Plan (everyone)
Create Test Cases (everyone)
Run Test Case (everyone)
Debug Sessions (pair programming teams)
Prepare for PM Review (everyone)
Deploy to cloud (TB-JX)
DU (PM)
PM Review (everyone)
It.1 debrief (PM)

## Slide 11
Iteration 2 (3/10 – 16/10)
Starting and clearing rounds Feature
Bid for a Section Feature
Drop Bid Feature
Integration
AWS Integration
Update Test Case (Everyone)
Run Test cases (Everyone)
Planned Debug Time (Pair Programming Teams)
DU (PM)
Prepare for Application Demo and Progress update (Everyone)
Application Demo and Progress update (Everyone)
It.2 Debrief (PM)
(Pair Programming Teams)

## Slide 12
Iteration 3 (17/10 – 30/10)
Drop a section Feature
View Bidding Results
Integration
Update Test Cases (Everyone)
Run Test Cases (Everyone)
Planned Debugging Time (Pair Programming Teams)
UI Design (Pair Programming Teams)
DU (PM)
Prepare for UAT (Everyone)
UAT (Everyone)
It.3 Debrief (PM)
(Pair Programming Teams)

## Slide 13
Iteration 4 (31/10 – 13/11)
Fix Problems from UAT (Pair Programming Teams)
Improve on UI Design (Pair Programming Teams)
Update Test Cases (Everyone)
Run Test Cases (Everyone)
Planned Debugging Time (Pair Programming Teams)
Prepare Final Presentation Slides (Everyone)
DU (PM)

## Slide 14
Iteration 5 (14/11 – 20/11)
DU (PM)
Presentation Rehearsal (Everyone)
Submission of Slides (Everyone)
Final Presentation (Everyone)

## Slide 15
Critical path Iter.1
1 | 1 | 1
Plan the project |  | 
1 | 5 | 6
1 | 6 | 6
Login Feature |  | 
1 | 0 | 6
1 | 6 | 6
Admin Feature |  | 
1 | 0 | 6
1 | 14 | 14
Daily DU |  | 
1 | 0 | 14
7 | 1 | 7
Create Test Plan |  | 
7 | 0 | 7
7 | 1 | 7
Create Test Cases |  | 
7 | 0 | 7
7 | 1 | 7
Run Test Cases |  | 
7 | 0 | 7
8 | 3 | 10
Planned Debugging Time |  | 
8 | 0 | 10
11 | 2 | 12
Prepare for PM Review |  | 
11 | 0 | 12
13 | 1 | 13
Deploy to Cloud |  | 
13 | 0 | 13
13 | 2 | 14
Submission of Project slides |  | 
13 | 0 | 14
14 | 1 | 14
PM Review |  | 
14 | 0 | 14
14 | 1 | 14
Iteration 1 Debrief |  | 
14 | 0 | 14

## Slide 16
Critical path Iter.2
1 | 4 | 4
Clearing rounds feature (round 1) |  | 
1 | 0 | 4
1 | 4 | 4
Bid for a section feature (round 1) |  | 
1 | 0 | 4
1 | 5 | 5
Criteria for bidding |  | 
1 | 0 | 5
1 | 14 | 14
Daily Update |  | 
1 | 0 | 14
5 | 1 | 5
Clearing rounds feature (round 2) |  | 
5 | 0 | 5
5 | 1 | 5
Bid for a section feature (round 2) |  | 
5 | 0 | 5
6 | 3 | 8
Drop bid feature |  | 
6 | 0 | 8
9 | 1 | 9
Integration |  | 
9 | 0 | 9
10 | 4 | 13
Prepare for Application Demo and Progress Update |  | 
10 | 0 | 13
10 | 4 | 13
Debugging time |  | 
10 | 0 | 13
9 | 1 | 9
Run test cases |  | 
9 | 0 | 9
9 | 1 | 9
Update test cases |  | 
9 | 0 | 9
9 | 1 | 9
AWS integration |  | 
9 | 0 | 9
14 | 1 | 14
Iteration 2 debrief |  | 
14 | 0 | 14
14 | 1 | 14
Application demo and progress update |  | 
14 | 0 | 14

## Slide 17
Critical path Iter.3
1 | 1 | 1
Drop a Section Feature |  | 
1 | 0 | 1
1 | 1 | 1
View Bidding Results |  | 
1 | 0 | 1
1 | 14 | 14
Daily DU |  | 
1 | 0 | 14
2 | 1 | 2
Integrate |  | 
2 | 0 | 2
3 | 1 | 3
Update Test Cases |  | 
3 | 0 | 3
4 | 1 | 4
Run Test Cases |  | 
4 | 0 | 4
5 | 3 | 7
Planned Debugging Time |  | 
5 | 0 | 7
8 | 1 | 8
UI Design |  | 
8 | 0 | 8
9 | 5 | 13
Prepare for UAT |  | 
9 | 0 | 13
14 | 1 | 14
UAT |  | 
14 | 0 | 14
14 | 1 | 14
Iteration 3 Debrief |  | 
14 | 0 | 14

## Slide 18
Critical path Iter.4
1 | 1 | 1
Fix problems from UAT |  | 
1 | 0 | 1
1 | 14 | 14
Daily update |  | 
1 | 0 | 14
2 | 3 | 4
Improve on UI design |  | 
2 | 0 | 4
5 | 1 | 5
Update test cases |  | 
5 | 0 | 5
6 | 1 | 6
Run test cases |  | 
6 | 0 | 6
7 | 1 | 7
Debugging time |  | 
7 | 0 | 7
8 | 7 | 14
Final presentation slides |  | 
8 | 0 | 14

## Slide 19
Critical path Iter.5
1 | 4 | 4
Submission of Slides |  | 
1 | 0 | 4
1 | 6 | 6
Presentation Rehearsal |  | 
1 | 0 | 6
7 | 1 | 7
Final Presentation |  | 
7 | 0 | 7
1 | 4 | 4
Daily DU |  | 
1 | 0 | 4

## Slide 20
3. Bug Metrics

## Slide 21: Bug Metrics
Total No. Of Bugs: 13
Bugs No. Range | Total Points
1 - 2 | 15
3 - 7 | 21
8 - 12 | 15
Action Taken: Stop task, schedule for debugging session for 8 hours with the responsible pair programmer (this includes asking for help from friends)

## Slide 22
4. Roles & Responsibilities

## Slide 23: Roles & Responsibilities
Rotation
Weeks | Project Manager
5 - 7 | Andrew
7 - 9 | Thao
9 - 11 | Jiaxin
11 - 13 | Jia Hui
14 | Zhen Hui

## Slide 24
5. Pair Programming

## Slide 25: Pair Programming
Weeks | Pair Programmer 1 | Pair Programmer 2
5-7 | Zhen Hui, Jiaxin | Thao, Jia Hui
7-9 | Zhen Hui, Andrew | Jiaxin, Jia Hui
9-11 | Thao, Andrew | Zhen Hui, Jia Hui
11-13 | Andrew, Jiaxin | Thao, Zhen Hui

## Slide 26: THANK YOU !